## Title Page
Group Number: | 21 | Sprint Number: | 2

## Product Backlog - EXAMPLE
Project Number | 6
Project Name: | UNCC Gaming Manager
Description: | Allows UNCC students who play video games to find and compete against other UNCC students looking to do the same. Host a tournament system where students cancompete against one another. Provide a platform that keeps track of Standings, Statistics, and User Preferences
Team Members
Story # | Card Front | Card Back | Assigned To | Comments
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality>
ST - 1 | As a UNCC student, I need to be able to use my UNCC credentials so that I can use the website. | Logged into web site
ST - 2 | As a UNCC student, I want to be able to search by platform, so that I can search for a match. | Searching on an entered search term categorized by Platform, returns results reflecting the search term(s)
ST - 3 | As a UNCC student, I want to be able to search game titles, so that I can search for a match. | Searching on an entered search term categorized by Game Titles returns results reflecting the search term(s)
ST - 4 | As a UNCC student, I want to be able to chat with the student I am matched with, so we can arrange the game. | Implement a working chat bar
ST - 5 | As a Moderator and a UNCC student, I want the website to load quickly, so I don't waste time. | Less than 5 second load time between pages
ST - 6 | As a Moderator, I want the site to also contain video game related news | Implement a News page
ST - 7 | As a Moderator, I want our website database to be secure, so that the users passwords are safe. | Site encryption, SSO, is enabled.
ST - 8 | As a UNCC student I would like to implement a tournament system | Implement a tournament system for up to 1028 players. Requirements are modeled after "March Madness" tournament brackets.
ST - 9 | As a UNCC student, I would like the layout to be clean, so that I can easily navigate it. | Web Standards and Usability Guidelines from https://webstandards.hhs.gov/guidelines/ are implemented accuractely.
ST - 10 | As a UNCC student, I would like to be able to create an account, so I can save my preferences. | Profile page implemented
ST - 11 | As a Moderator, I would like the page to contain a list of popular games | Implement a table in the dataase to track them
ST - 12 | As a Moderator, I first time users to see a first time tutorial after signing up | Tutorial splashscreen after user creation

## Product Backlog
PRODUCT BACKLOG
Project Number | 21
Project Name: | Parrot Post
Description: | Allows users to connect to a comminucation service with their peers and post/view announcements, post/view calendar events, search their contacts, view and edit their profile page, view other documents, and change settings.
Team Members | Landon Leigh, Tim Mathis, Matt Bavis, Silas Edrington, Saim Woldu
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Changes made since last submission | Estimated Size (SML) | Estimated Size (Hours) | Actual Hours | Estimated Velocity
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality>
ST-1 | As an organization member I need to be able to log into the app using credentials so that, without it a user cant login | Logged into app | 2 | 2 | Silas | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | S | 2 | Not finished
ST-2 | As an organization member I need to be able to view upcoming meetings in a calander so that users are able to view upcoming events | Can view Calander | 2 & 3 | 3 | Landon | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | L | 9 | 3
ST-3 | As an organization member I need to be able to create, edit, and share events so that, If someone holds a position they need to be able to create meeting times and events | can create,edit and share events inside and outside of organization | 2 | 4 | Tim | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | M | 5 | 2
ST-4 | As an organization memeber I need to be able to view information about my organization so that viewing important documents like absence forms are needed to properly operate an organization | Organizations have info such as names, admins, etc that anyone inside org has access to | 3 | 9 | Silas | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | S | 2 | not finished
ST-5 | As an organization leader I need to be able to manage who is in my organization so that anyone should be able to see whos in their organization and contact them in a neat way, moderators should be able to edit these list | Can view and edit list of organization members | 3 | 6 | Saim | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | S | 2 | 2
ST-6 | As an organization memeber I need to be able to contact other members inside/outside of my organization so that without a neat organization of their contact info, getting that info in the first place and be difficult or even keeping track of all the names and numbers | Organization members have email adresses that can be used for professional contacts | 2 | 7 | Landon | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | S | 2 | not finished
ST-7 | As an organization member, I would like to be able to create an account so that, if I am apart of the org, I would like to have an account to view what is happening | Profile page implemented | 2 | 1 | Matt | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | M | 5 | not finished
ST-8 | As an organization member, I would like the layout to be neat an easy to navigate so that if the app is easy to use then a user is more likely to use it | Web Standards and Usability Guidelines from https://webstandards.hhs.gov/guidelines/ are implemented accuractely. | 2 & 3 | 10 | Saim | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | M | 5 | 5
ST-9 | As an organization member, I want to be able to quickly load and view pages on the app so that if an app is slow and time consuming to use no user will want to use it | Quick load times | 3 | 15 | Matt | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | S | 2 | not finished
ST-10 | As an organization member, I want to be able to add polls to get feedback from other members so that as organization we want to be able to vote democratically and get opinions on issues so polling is needed | Polling and voting implemented | 3 | 8 | Tim | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | L | 9 | not finished
ST-11 | As a moderator, I want to be able to oversee posts and polls and take them down if necessary so that with moderators assigned, the apps announcements and events will not go to chaos like discord and twitch chats do sometimes | Moderator permissions implemented | 3 | 12 | Silas | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | S | 2 | not finished
ST-12 | As an organization member/moderator, I want to be able to post announcments to my members so that we can Post, Posting important information to inform the rest of the org is crucial in a communication app | Announcement to members implemented | 2 | 5 | Matt | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | M | 5 | 3 so far not finished
ST-13 | As a organization leader I want to be able to create a specific channel for my organization only so that the owner of the org should be able to buy a domain for the group so only that org can view its information. We dont want others not apart of our org able to see the announcements and information | Organization channels implemented | 3 | 11 | Landon | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | M | 5 | not finished
ST-14 | As an organization member I want to be able to message and contact org members so that when viewing a contact I should be able to click their number and choose to text or call popup so I can quickly contact a single person | message hyperlinks implemented | 3 | 14 | Tim | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | S | 2 | not finished
ST-15 | As an organization member I want to be able to click on the links to be able to navigate to other pages/websites so that, I click a persons linkedIn acct I want it to take me to his account | Hyperlinking implemented | 2 | 13 | Saim | Updated estimated hours to more accurately reflect how long it will take, added which sprint number it will be worked on in and the priority of it | S | 2 | 1
[7 empty] | Story Point Key | Hours
[7 empty] | Small | 2
[7 empty] | Medium | 5
[7 empty] | Large | 9